## Sheet1
Timeline | Plan
|  | Date | Tasks
May 9th - June 8th | 1. Identify the crucial and most dependent requirements to satisfy. 2. Identify the hosting server, develop testing enviornment and databases. 3. Development of the application.
|  | 2016-05-06 | Formal Meeting with Nike and Basheer
|  | 2016-05-09 | Project Begin
|  | 9 May - 16 May | Understanding the requirements, prioritizing them and understanding the development enviornment.
June 9th - July 8th | Application Development | 16 May - 31 May | Understanding Katie's Course Management System structure and LoudCloud System. Developing the wire frames or mock up pages
|  | June 1 - June 7 | Development and frame diagrams or screen mock ups
|  | June 7 - June 24 | Development and Web pages
|  | June 24 - Jun30 | Development and Web pages
July 9th - August 8th | Finializing application development, testing the application and integrating the application with the current course management system. | 2016-07-01 | Partial Ouput. Set up temporary website or localhost for viewing the wesbsite.
|  | Jul 1 - Jul 7 | Development and Web pages
|  | Jul 7 - Jul 14 | Development and Web pages
|  | Jul 7 - Jul 21 | Development and Web pages
|  | 2016-07-21 | Partial Ouput
|  | Jul 21 - Jul 31 | Testing
|  | Aug 1 - Aug 8 | Testing and Deployment
****We will have a weekly meetings to understand the team position and work progress. Day and Time - Every Monday 6:30 AM